## Sheet1
CNC Commissioning Time Line
Week Commencing on Sunday | Date to be set | 2016-07-03 | 2016-07-10 | 2016-07-17 | 2016-07-24 | 2016-07-31 | 2016-08-07 | 2016-08-14 | 2016-08-21 | 2016-08-28 | 2016-09-04 | 2016-09-11 | 2016-09-18 | 2016-09-25 | 2016-10-02 | 2016-10-09 | 2016-10-16 | 2016-10-23 | 2016-10-30 | 2016-11-06 | 2016-11-13 | 2016-11-20 | 2016-11-27 | 2016-12-04 | 2016-12-11 | 2016-12-18 | 2016-12-25 | 2017-01-01
3 phase power
|  | complete tidy of CNC pit | Clear & organise Timber Store | Delivery and install by vendor |  | Full Risk Assessment | Safe Work Procedures
| Designing For CNC | 2016-07-03: 3 phase power install; 2016-07-10: Build acoustic wall; 2016-07-17: Training ?; 2016-08-07: Draft Induction
|  |  | School Visit | Interim Risk Assessment |  |  | Test Induction
| Photos | 2016-07-17: Test Projects ready for cutting (for training/ Famil Days; 2016-07-24: 2 Days Training and Famil of machine; 2016-09-18: First Public CNC induction; 2016-09-25: CNC Induction; 2016-10-02: CNC Induction; 2016-10-09: CNC Induction; 2016-10-16: CNC Induction; 2016-10-23: CNC Induction; 2016-10-30: CNC Induction; 2016-11-06: CNC Induction; 2016-11-13: CNC Induction; 2016-11-20: CNC Induction; 2016-11-27: CNC Induction
| Blog Posts | 2016-09-04: 1st Cubby House Project to start; 2016-11-27: All Cubby houses cut and ready for delivery
| Media | 2016-07-17: Materials arrive for test projects
Build acoustic wall
Identify materials handling needs