Reflection on Delivery of Workshops at Woodford 201617

Locks

Positives	Negatives
Punters loved the workshop	The Instructions need more work. Perhaps broken up into more stages. Photos on a yellow background do not contrast well with the small parts.
Most people finished	We need to perhaps go back and look at the design as a whole. The many small plastic parts have resolved some issues with the limitation of cardboard engineering. But this has left us with a huge number of small parts to content with (about 70?).
Nearly enough kits to handle the over booking	The springs needed more trimming
	Not every one agrees but it would be good to see an acrylic model with a key to demonstrate how it works.
	This workshop required large amount of prep hours
	Not enough rolls of tape at the workshop

Windup LED

Positives	Negatives
Punters loved the workshop	There were concerns about the waste from packaging
	The nut traps were not etched out deep enough
	It would be good to change the winding direction to clock wise direction – against the thread of the bolt
	There were concerns about the realitively long prep hours
	It would have been good to have a demo model to show people what they were making
Most people finished 95 completion

Miscellaneous Comments

Positives	Negatives
The lighting was an improvement on last year but there is still a way to go	No: of participants was not ideal for these types of workshops
It was great to take less gear this year	We are still attracting lots of little kids
It was good to have enough helpers this year	There was lots of ambient noise next to the small hall – maybe there is an argument for some amplification of the facilitator
It was a good first step to have wifi in the workshops space this year	It was a little complicated for participants to navigate to the instructions on our website
	The projector was underpowered and out in the middle of the room. Would be good to take the ultra short throw projector next time
	It would be good to have a consistent Edge intro, and look and feel for the instructions / presentation.
	We need to always pack spare kits
	The idea of selling kits at the mech stand was discussed
	The Idea of having trays (magnetic ) for people to put the small parts was discussed.